[Project Name] Planning Checklist

| Project Manager | [name] |
| --- | --- |

| Risk Management |  |
| --- | --- |
|  | The project team has invested time and energy into identifying all project risks. |
|  | A risk response strategy has been developed for all risks that have a significant impact or probability. |
|  | Contingency funds or time have been allocated by management. |
|  | Funds to account for unexpected problems have been set aside as Management Reserve. |
|  | A risk log has been developed to manage known risks and is accessible to all project team members. |
|  | Every risk in the log has someone responsible for managing it. |
|  | There is a plan in place for continuously identifying and responding to new risks. |

| Work Breakdown Structure |  |
| --- | --- |
|  | Tasks have been identified to produce every deliverable in the statement of work. |
|  | The work breakdown structure for the project is consistent with standard WBS guidelines and/or templates for similar projects. |
|  | The project team participated in building the WBS or has reviewed and approved it. |
|  | Every task on the WBS has a strong, descriptive name that includes a noun and a verb. |
|  | Every task on the WBS has a beginning, an end, and clear completion criteria. |
|  | Project management tasks are included on the WBS. |
|  | Tasks have been broken down to a level that enables clear responsibility to be assigned. |
|  | The WBS follows the rules for creating a top-down decomposition. |
|  | The structure of the WBS has been evaluated to ensure the summary tasks are meaningful to stakeholders that require high-level understanding of the project. |

| Task Sequence |  |
| --- | --- |
|  | All work packages have predecessor tasks identified and task relationships are illustrated using a network diagram. |
|  | The team has reviewed all predecessor-successor relationships to ensure there are none missing and that none of the relationships are unnecessary. |
|  | Only work packages have predecessor-successor relationships defined. These relationships are not defined for summary tasks. |
|  | External schedule constraints are represented by milestones. |

| Estimating |  |
| --- | --- |
|  | Wherever possible, historical data has been used as the basis for estimating. |
|  | Ball park estimates have only been used for initial screening and are not the basis for setting any project baselines. |
|  | Estimates have been prepared by people who understand how to perform the work and who understand the constraints of the people who will perform the work. |
|  | Work package estimates include both the duration and the estimated labor. |

| Scheduling |  |
| --- | --- |
|  | Critical path analysis has been performed to identify critical path tasks and schedule float. |
|  | Resource leveling has been applied to ensure the schedule represents a realistic allocation of personnel and other resources. |
|  | The schedule is based on realistic assumptions about the availability of project personnel. |
|  | Portions of the schedule that contain many concurrent tasks have been evaluated for risk. |
|  | The cost-schedule-quality equilibrium is realistic and acceptable to the customer. |

| Vendors and sub-contractors |  |
| --- | --- |
|  | Vendors and sub-contractors have signed contracts with specific scopes of work. |
|  | The work to be performed by vendors and sub-contractors is integrated into the WBS and schedule. |
|  | There are specific milestones and activities planned for monitoring vendors and sub-contractors. |

| Approvals |  |
| --- | --- |
|  | The detailed action plan has been presented and approved. |