## Sheet1
Audience | Vehicle of Communicaiton | Frequency | Medium | Source | Delivered by | Sensitivities | Date Delivered | Expected Result
Project Managers the PMO will serve | One-on-one meetings | Upon arrival at client | verbal | Contract | PMO Manager | employee turnover, prior experience with PMO, perception of beauracracy | October, November | Educate project managers and understand what some of there expectations may be; get everyone on the same page
Project Managers the PMO will serve | PMO Kickoff meeting | as requested; major milestones | presentation | Contract | PMO Manager | employee turnover | 1999-11-29 | Bring everyone together and intitiate the PMO status meetings, review goals/objs, answer questions
CIO direct reports | Informal Meeting - PMO objectives | At PMO initiation, other major changes such as new project, they join, etc. | verbal | Contract | PMO Manager | Is this another bottleneck? How does my role fit in here? | November, December | Discussion regarding the PMO, what it is, who is part of it, and Question / Answer time; get everyone on the same page
CIO general public | Newsletter? | PMO announcement | email (intranet posting?) | Contract | PMO Manager | Is this another bottleneck? | January | Educate them on what a PMO provides
Executive Staff? | Executive Staff One-on-Ones | PMO Announcement | staff meeting? | Contract | PMO Manager |  |  | Educate them on what a PMO provides
Strategic Business Unit leads? | one-on-ones | PMO announcement, and as they initiate projects supported by CIO group. |  | Contract | PMO Manager | If it came out of CSS, can it be any good? | January/ February | Educate them on what a PMO provides, as well as help them determine if a PMO infrastructure would serve well on the business side as well.
Immediate project management | PMO Meetings | bi-weekly | presentation | project statuses, PMO status | PMO Manager |  | 3/2/98 and weekly thereafter | Identify/resolve issues; communicate info from management team meetings
CIO | PMO Status report | Monthly | email to CIO, project managers that are part of the PMO | Weekly status reports | Consultant |  | Last Thursday of every month | Provide status of tasks, budget and timeline; identify major issues
Department leads that work with the BPMs: David Harris, Jennifer Haase, Cynthia Currance | Informal Meeting - PMO Goals and objectives | At PMO initiation, other major changes such as new project, they join, etc. | verbal | Contract | PMO Manager | CSS experience (good and bad) | December, January | Educate them on what a PMO provides
Project team, anyone you run into, IN THE ELEVATOR or hallways | Elevator conversations | Establish at project initiation; revisit at any major scope/timeline changes | hardcopy; LAN |  | Consultant |  | as needed | Speak to the specific business problem the project will address, who it impacts (business and technical), the different groups involved, locations to be implemented
Organization | FAQ's | Evolving document; usually updated when major issues are resolved | hardcopy; LAN/WEB |  | Consultant |  | as needed | Answer frequently asked questions about the project
Organization | Seffrin weekly update |  | hardcopy; LAN/WEB |  | Consultant |  |  | Public announcements regarding project impact, major accomplishments
Organization | "Brownbag Lunches" | At project initiation, major revisions and/or scope change | hardcopy; LAN/WEB |  | Consultant |  |  | Communicate in an informal manner regarding technology and business impact of the project
Business Team | Informal meeting - Project Plan | At kickoff, major revisions and/or scope change | hardcopy, email |  | Consultant |  | as needed | Address dependencies between technical schedule and warehouse readiness
All Stakeholders | Change Management procedures | Scope change | meeting
Note on A1: Who will you be addressing? Review the list of attendees to understand what broad-base level of understanding exists for the topic you will be discussing. Have they heard the message before? Is there a previous presentation given to them that should be referred to/reviewed as part of the current presentation being developed?
Note on B1: What are the different types of communication being used throughout the organization? Examples: Corporate Reports Divisional Newsletters NHO Reports Weekly Status Reports Steering Committee Mtgs ISLE Mtgs etc…
Note on C1: Identify the frequency at which this communication will occur; can use dates, days/week (e.g. every fourth Thursday, first Friday of every month, etc.)
Note on D1: What will be the method used to communicate: - Powerpoint Presentation (hardcopy or presented on an overhead - big difference!) - Email - Newsletter - Hardcopy -
Note on E1: Identify the source of the information used to develop the communication
Note on F1: Identify who will deliver the presentation
Note on G1: Analyze the audience for any sensitivities that may be adversely affected by the communication: - Disagreement with approach - Haven't heard what is being delivered in the the communication before - If negative news is a part of the communication, do some members of the audience need to know before hand? - What has the audience heard before - Review the vehicle, delivery person and medium: is it appropriate given the sensitivities?
Note on H1: Identify dates (even if multiple) that this communication has been delivered.
Note on I1: Clearly identify goals/objectives of the communication, and if the result was achieved.